## Master Plan (hidden)
Master Plan
| Project ID |  |  | -
| Project Name |  |  | RPA(Robotic Program Automation_UiPath)
| Project Duration |  |  | DAT need to make proposal.
| Project Summary |  |  | Create project for DIR Environment by applying UiPath. RPA means Robotic Process Automation. One of the benefits of RPA is it can be used to automate tasks in any industry, including insurance, healthcare, banking and financial services, procurement, supply chain management, and manufacturing. UiPath is powerful RPA platform for fast and highly scalable automation.
| Project Manager |  |  | Pwint Mar Naing Win(Pyae Pyae)
Risk Factors
Lack of required domain knowledge
Lack of technological background
Feasibility of selected technology
Lack of requirement understanding
Requirement misunderstanding
Lack of documentation knowledge
Lack of problem solving skill
Thin Client usage difficulties
Project Volume
|  | Working hours per day |  |  | : | 7 | hr
|  | Working days per month |  |  | : | 20 | days
|  | 20 days |  |  | : | 1 | man-month
|  | 1 day |  |  | : | 0.05 | man-month
|  | Project Period |  |  | : | 789.5 | days
|  | Total Man-Month |  |  | : | 39.475 | man-month (without risk)
[8 empty] | Man-Month |  |  | Man-Day
|  | Phase | [5 empty] | Work | Review and Mgt | Total | Work | Review and Mgt | Total
|  | 01 - Preparation for project(Learning UiPath) | [5 empty] | 12.5 | 0 | 12.5 | 250 | 0 | 250
|  | 02 - Sample Project Creation | [5 empty] | 1.5 | 0.45 | 1.95 | 30 | 9 | 39
|  | 03 - Environment Setup on Thin Client | [5 empty] | 0.25 | 0 | 0.25 | 5 | 0 | 5
|  | 04 - Run Sample Project at Thin Client | [5 empty] | 0.25 | 0.075 | 0.325 | 5 | 1.5 | 6.5
|  | 05- Learn Requirement Definition & Translation | [5 empty] | 0.4 | 0.12 | 0.52 | 8 | 2.4 | 10.4
|  | 05 -DIR Project | [5 empty] | 18.1 | 5.43 | 23.53 | 362 | 108.6 | 470.6
|  | 06- Run DIR Project at Thin Client | [5 empty] | 0.4 | 0 | 0.4 | 8 | 0 | 8
|  | Sub Total (man-month) | [5 empty] | 33.4 | 6.075 | 39.475 | 668 | 121.5 | 789.5
|  | Risk (10%) | [7 empty] | 3.9475 |  |  | 78.95
|  | Total (man-month) | [7 empty] | 43.4225 |  |  | 868.45
[10 empty] | 43.4225 |  |  | 868.45
Schedule with 8 HR
2017
[7 empty] | Month | 1st(Oct) |  | 2nd(Nov) |  | 3rd(Dec) |  | 4th(Jan) |  | 5th(Feb) |  | 6th(March) |  | 7th(April)
[7 empty] | Week | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th | 1st-2nd | 3rd-4th
Phase
01 - Preparation for project(Learning UiPath)
02 - Sample Project Creation
03 - Environment Setup on Thin Client
04 - Run Sample Project at Thin Client
05- Learn Requirement Definition & Translation
05 -DIR Project
06- Run DIR Project at Thin Client
|  | Total Man-Month | [5 empty] | 3.5 |  | 7 |  | 11.5 |  | 7 |  | 7 |  | 7
43

## WBS
WBS (Virtual Card System Development) | [23 empty] | 2018-04-01 | [29 empty] | 2018-05-01 | [30 empty] | 2018-06-01 | [29 empty] | 2018-07-01 | [30 empty] | 2018-08-01 | [30 empty] | 2018-09-01 | [29 empty] | 2018-10-01 | [30 empty] | 2018-11-01
| Status | WBS No. and Task Description |  |  |  |  | Status | Assignee % |  | Plan Start | Plan Finish | Work (days) | Work (hour) | Predecessor | Actual Start | Actual Finish | Actual Work (hour) | Actual Work (days) | Forward / Delay | Expected Outputs | Comment / Delay Reason | plan hr | actual hr | time axis 2018-04-01 to 2018-11-14
[22 empty] | plan hr | actual hr | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | H | H | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | H | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | Fri | H | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | H | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | Fri | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | H | H | H | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | Fri
PHASE IV_Lot 1 (DA Change)
|  | P2_1 | Preparation for project(RD and Message Confirmation)
a | Finished |  | P2_1.1 | Investigate Project Scope | [17 empty] | 0 | 0
a | Finished |  |  | VCS Mobile Requirement Design & Process Flow Confirmation | [17 empty] | 0 | 0
| Finished |  |  | P1_1.1.1 | Digital Application Apply |  | 100% | PWH | 100% | 2020-01-28 | 2020-01-30 | 3 | 21 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 62 days
| Finished |  |  | P1_1.1.2 | Digital Application List |  | 100% | PWH | 100% | 2020-01-28 | 2020-01-30 | 3 | 21 hr
| Finished |  |  | P1_1.1.3 | Digital Application Detail |  | 100% | PWH | 100% | 2020-01-28 | 2020-01-30 | 3 | 21 hr
| Finished |  |  | P1_1.1.4 | Modification of QR Code Creation + Product List Popup and Confirm/Cancel Purchasing |  | 100% | PWH | 100% | 2020-01-28 | 2020-01-28 | 1 | 7 hr
| Finished |  |  | P1_1.1.5 | Multi Login |  | 100% | PWH | 100% | 2020-01-31 | 2020-01-31 | 1 | 7 hr
| Finished |  |  | P1_1.1.6 | Menu for Digital Application + Menu Notification |  | 100% | PWH | 100% | 2020-01-31 | 2020-01-31 | 1 | 7 hr
| Finished |  |  | P1_1.1.7 | Loan Calculator |  | 100% | PWH | 100% | 2020-03-12 | 2020-03-12 | 1 | 7 hr
a | Finished |  |  | ASS Mobile Requirement Design & Process Flow Confirmation | [17 empty] | 0 | 0
| Finished |  |  | P1_1.1.8 | QR Scan |  | 100% | PWH | 100% | 2020-02-03 | 2020-02-04 | 2 | 14 hr |  | 2019-09-16 | 2019-09-16 |  | 1 day | 91 days
| Finished |  |  | P1_1.1.9 | DA Modification |  | 100% | PWH | 100% | 2020-02-03 | 2020-02-04 | 2 | 14 hr |  | 2019-09-19 | 2019-09-20 |  | 2 days | 87 days
| Finished |  |  | P1_1.1.10 | Member Photo Taken |  | 100% | PWH | 100% | 2020-02-03 | 2020-02-04 | 2 | 14 hr |  | 2019-09-23 | 2019-10-01 |  | 7 days | 80 days
| Finished |  |  | P1_1.1.11 | Product Purchase |  | 100% | PWH | 100% | 2020-02-05 | 2020-02-05 | 1 | 7 hr |  | 2019-09-25 | 2019-10-01 |  | 5 days | 81 days
| Finished |  |  | P1_1.1.12 | Upload Photo for Aeon Checking |  | 100% | PWH | 100% | 2020-02-05 | 2020-02-06 | 2 | 14 hr |  | 2019-09-27 | 2019-10-01 |  | 3 days | 82 days
| Finished |  |  | P1_1.1.13 | Photos Attached |  | 100% | PWH | 100% | 2020-02-05 | 2020-02-06 | 2 | 14 hr |  | 2019-10-01 | 2019-10-01 |  | 1 day | 82 days
| Finished |  |  | P1_1.1.14 | Product Purchase Document Edit Followup |  | 100% | PWH | 100% | 2020-02-05 | 2020-02-05 | 1 | 7 hr |  | 2019-10-02 | 2019-10-02 |  | 1 day | 80 days
| Finished |  |  | P1_1.1.15 | Product Purchase Cancel |  | 100% | PWH | 100% | 2020-02-06 | 2020-02-06 | 1 | 7 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 80 days
| Finished |  |  | P1_1.1.16 | Product Purchase List |  | 100% | PWH | 100% | 2020-02-07 | 2020-02-07 | 1 | 7 hr |  | 2019-11-01 | 2019-11-04 |  | 2 days | 63 days
| Finished |  |  | P1_1.1.17 | Application Status List |  | 100% | PWH | 100% | 2020-02-10 | 2020-02-10 | 1 | 7 hr
| Finished |  |  | P1_1.1.18 | Loan Calculator |  | 100% | PWH | 100% | 2020-03-12 | 2020-03-12 | 1 | 7 hr
a | Finished |  |  | DA WEB Admin | [17 empty] | 0 | 0
| Finished |  |  | P1_1.1.19 | LGN001 |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-09-09 | 2019-09-09 |  | 1 day | 103 days
| Finished |  |  | P1_1.1.20 | MNU001 |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-09-10 | 2019-09-10 |  | 1 day | 102 days
| Finished |  |  | P1_1.1.21 | MAN001 (Dashboard) |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-10-09 | 2019-10-17 |  | 4 days | 78 days
| Finished |  |  | P1_1.1.22 | USR001 |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-09-10 | 2019-09-10 |  | 1 day | 102 days
| Finished |  |  | P1_1.1.23 | USR002 |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-09-11 | 2019-09-11 |  | 1 day | 101 days
| Finished |  |  | P1_1.1.24 | USR003 |  | 100% | PWH | 100% | 2020-02-11 | 2020-02-13 | 2 | 14 hr |  | 2019-09-12 | 2019-09-12 |  | 1 day | 100 days
| Finished |  |  | P1_1.1.25 | USR004 |  | 100% | PWH | 100% | 2020-02-14 | 2020-02-14 | 1 | 7 hr |  | 2019-09-13 | 2019-09-13 |  | 1 day | 100 days
| Finished |  |  | P1_1.1.26 | USR005 |  | 100% | PWH | 100% | 2020-02-14 | 2020-02-14 | 1 | 7 hr |  | 2019-09-14 | 2019-09-14 |  | 0 days | 99 days
| Finished |  |  | P1_1.1.27 | USR006 |  | 100% | PWH | 100% | 2020-02-14 | 2020-02-14 | 1 | 7 hr |  | 2019-09-15 | 2019-09-15 |  | 0 days | 99 days
| Finished |  |  | P1_1.1.28 | USR007 |  | 100% | PWH | 100% | 2020-02-14 | 2020-02-14 | 1 | 7 hr |  | 2019-09-16 | 2019-09-16 |  | 1 day | 99 days
| Finished |  |  | P1_1.1.29 | USR008 |  | 100% | PWH | 100% | 2020-02-14 | 2020-02-14 | 1 | 7 hr |  | 2019-09-17 | 2019-09-17 |  | 1 day | 98 days
| Finished |  |  | P1_1.1.30 | APL001 (List / Cancel) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-09-25 | 2019-09-27 |  | 3 days | 115 days
| Finished |  |  | P1_1.1.31 | APL002 (Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-09-30 | 2019-10-02 |  | 3 days | 112 days
| Finished |  |  | P1_1.1.32 | APL003 (Application List for New Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 111 days
| Finished |  |  | P1_1.1.33 | APL004 (Application List for Indexed Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 111 days
| Finished |  |  | P1_1.1.34 | APL005 (Application List for Uploaded Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-04 | 2019-10-04 |  | 1 day | 110 days
| Finished |  |  | P1_1.1.35 | APL006 (Application List for Cancel Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-04 | 2019-10-04 |  | 1 day | 110 days
| Finished |  |  | P1_1.1.36 | APL007 (Application List for Document Follow Up Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 109 days
| Finished |  |  | P1_1.1.37 | APL008 (Application List for Settled Index Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 109 days
| Finished |  |  | P1_1.1.38 | APL009 (Application List for Settled Application) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 109 days
| Finished |  |  | P1_1.1.39 | APL0010 (New Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-04 | 2019-10-07 |  | 2 days | 109 days
| Finished |  |  | P1_1.1.40 | APL0011 (Indexing Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 109 days
| Finished |  |  | P1_1.1.41 | APL0012 (Application Upload Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-08 | 2019-10-08 |  | 1 day | 108 days
| Finished |  |  | P1_1.1.42 | APL0013 (Application Edit Request Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-09 | 2019-10-09 |  | 1 day | 107 days
| Finished |  |  | P1_1.1.43 | APL0014 (Settlement Indexing Detail) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-10 | 2019-10-10 |  | 1 day | 106 days
| Finished |  |  | P1_1.1.44 | APL0015 (Upload Photo Check by Aeon) |  | 100% | PWH | 100% | 2020-02-14 | 2020-03-20 | 24 | 168 hr |  | 2019-10-10 | 2019-10-17 |  | 3 days | 104 days
a | Not Started Yet |  | P2_1.3 | Create Requirement Definition Specification |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.4 | Create HTML Mock (WEB) |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.5 | R&D for Google Map |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.6 | Create HTML Mock (Mobile) |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.7 | Mobile Requirement Design & Process Flow Confirmation |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.8 | WEB Requirement Design & Process Flow Confirmation |  |  |  |  | 100%
a | Not Started Yet |  | P2_1.9 | Postman Acc Creation |  |  |  |  | 100%
|  | P2_2 | Request to AEON
a | Cancel |  | P2_2.1 | News/Promotion Contents |  |  |  |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_2.2 | Confirm "Promotion" title |  |  |  |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_2.3 | Apple Developer Account Activation |  |  |  |  | 100% | [12 empty] | 0 | 0
|  | P2_3 | Design
a | Not Started Yet |  | P2_3.1 | Logical ERD Update |  |  |  |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_3.2 | DDL/DML Update |  |  |  |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_3.3 | Item Definition |  |  |  |  | 100% | [12 empty] | 0 | 0
a |  | P2_4 | Coding Development
a | Finished |  | P2_4.1 | Coding Development(Andriod) | [17 empty] | 0 | 0
| Finished |  |  | 4.1.1 | Digital Application Apply |  | 100% | MTT | 100% | 2020-02-10 | 2020-02-19 | 7 | 49 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 76 days
| Finished |  |  | 4.1.2 | Digital Application List |  | 100% | MTT | 100% | 2020-02-20 | 2020-02-21 | 2 | 14 hr
| Finished |  |  | 4.1.3 | Digital Application Detail |  | 100% | MTT | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr
| Finished |  |  | 4.1.4 | Modification of QR Code Creation + Product List Popup and Confirm/Cancel Purchasing |  | 100% | MTT | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr
| Finished |  |  | 4.1.5 | Multi Login |  | 100% | AHO | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr
| Finished |  |  | 4.1.6 | Menu for Digital Application + Menu Notification |  | 100% | SSS | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr
| Finished |  |  | 4.1.7 | Loan Calculator |  | 100% | AHO | 100% | 2020-03-18 | 2020-03-19 | 2 | 14 hr
| Not Started Yet |  |  | 4.1.8 | Lv1 Cotact Us |  | 0% | AHO | 100% | 2020-04-20 | 2020-04-24 | 5
| Not Started Yet |  |  | 4.1.9 | Lv2 Cotact Us (Free Chat) |  | 0% | AHO | 100% | 2020-04-27 | 2020-04-30 | 4
| Not Started Yet |  |  | 4.1.10 | Ask Product |  | 0% | AHO | 100% | 2020-05-04 | 2020-05-11 | 5
a | Finished |  | P2_4.2 | Coding Development(iOS) | [17 empty] | 0 | 0
| Finished |  |  | 4.2.1 | Training for Project |  | 0% | KMS | 100% | 2020-03-30 | 2020-04-03 | 5 | 35 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 108 days
| Finished |  |  | 4.2.2 | Digital Application Apply |  | 0% | KMS | 100% | 2020-04-06 | 2020-04-21 | 6 | 42 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 120 days
| Finished |  |  | 4.2.3 | Digital Application List |  | 0% | KMS | 100% | 2020-04-22 | 2020-04-28 | 4.5 | 31.5 hr
| Finished |  |  | 4.2.4 | Digital Application Detail |  | 0% | KMS | 100% | 2020-04-28 | 2020-05-05 | 4.5 | 31.5 hr
| Finished |  |  | 4.2.5 | Modification of QR Code Creation + Product List Popup and Confirm/Cancel Purchasing |  | 0% | KMS | 100% | 2020-05-06 | 2020-05-12 | 5 | 35 hr
| Finished |  |  | 4.2.6 | Multi Login |  | 0% | KMS | 100% | 2020-05-13 | 2020-05-18 | 4 | 28 hr
| Finished |  |  | 4.2.7 | Menu for Digital Application + Menu Notification |  | 0% | KMS | 100% | 2020-05-19 | 2020-05-20 | 2 | 14 hr
| Finished |  |  | 4.2.8 | Loan Calculator |  | 0% | KMS | 100% | 2020-05-21 | 2020-05-25 | 3 | 21 hr
| Not Started Yet |  |  | 4.2.9 | Lv1 Cotact Us |  | 0% | KMS | 100% | 2020-05-26 | 2020-06-01 | 5
| Not Started Yet |  |  | 4.2.10 | Lv2 Cotact Us (Free Chat) |  | 0% | KMS | 100% | 2020-06-02 | 2020-06-05 | 4
| Not Started Yet |  |  | 4.2.11 | Ask Product |  | 0% | KMS | 100% | 2020-06-06 | 2020-06-10 | 4
a | Finished |  | P2_4.3 | Coding Development(WEB Service) | [17 empty] | 0 | 0
| Finished |  |  | 4.3.1 | Digital Application Apply |  | 100% | HWYK | 100% | 2020-02-10 | 2020-02-19 | 7 | 49 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 76 days
| Finished |  |  | 4.3.2 | Digital Application List |  | 100% | HWYK | 100% | 2020-02-20 | 2020-02-21 | 2 | 14 hr
| Finished |  |  | 4.3.3 | Digital Application Detail |  | 100% | HWYK | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr
| Finished |  |  | 4.3.4 | Modification of QR Code Creation + Product List Popup and Confirm/Cancel Purchasing |  | 100% | HWYK | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr
| Finished |  |  | 4.3.5 | Multi Login |  | 100% | HWYK | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr
| Finished |  |  | 4.3.6 | Menu for Digital Application + Menu Notification |  | 100% | HWYK | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr
| Finished |  |  | 4.3.7 | Loan Calculator |  | 100% | HWYK | 100% | 2020-02-18 | 2020-02-19 | 2 | 14 hr
| Not Started Yet |  |  | 4.3.8 | Lv1 Cotact Us |  | 100% | HWYK | 100% | 2020-04-03 | 2020-04-06 | 2
| Not Started Yet |  |  | 4.3.9 | Lv2 Cotact Us (Free Chat) |  | 100% | HWYK | 100% | 2020-04-07 | 2020-04-08 | 2
| Not Started Yet |  |  | 4.3.10 | Ask Product |  | 100% | HWYK | 100% | 2020-04-09 | 2020-04-20 | 2
a | Finished |  | P2_4.4 | Coding Development(ASS ) | [17 empty] | 0 | 0
| Finished |  |  | 4.4.1 | QR Scan |  | 100% | MTT | 100% | 2020-01-06 | 2020-01-09 | 4 | 28 hr |  | 2019-09-16 | 2019-09-16 |  | 1 day | 73 days
| Finished |  |  | 4.4.2 | DA Modification |  | 100% | MTT | 100% | 2020-01-10 | 2020-01-17 | 6 | 42 hr |  | 2019-09-19 | 2019-09-20 |  | 2 days | 75 days
| Finished |  |  | 4.4.3 | Member Photo Taken |  | 100% | MTT | 100% | 2020-01-20 | 2020-01-22 | 3 | 21 hr |  | 2019-09-23 | 2019-10-01 |  | 7 days | 71 days
| Finished |  |  | 4.4.4 | Product Purchase |  | 100% | MTT | 100% | 2020-01-23 | 2020-01-27 | 3 | 21 hr |  | 2019-09-25 | 2019-10-01 |  | 5 days | 74 days
| Finished |  |  | 4.4.5 | Upload Photo for Aeon Checking |  | 100% | MTT | 100% | 2020-01-28 | 2020-01-29 | 2 | 14 hr |  | 2019-09-27 | 2019-10-01 |  | 3 days | 76 days
| Finished |  |  | 4.4.6 | Photos Attached |  | 100% | MTT | 100% | 2020-01-30 | 2020-01-31 | 2 | 14 hr |  | 2019-10-01 | 2019-10-01 |  | 1 day | 78 days
| Finished |  |  | 4.4.7 | Product Purchase Document Edit Followup |  | 100% | MTT | 100% | 2020-02-03 | 2020-02-04 | 2 | 14 hr |  | 2019-10-02 | 2019-10-02 |  | 1 day | 79 days
| Finished |  |  | 4.4.8 | Product Purchase Cancel |  | 100% | MTT | 100% | 2020-02-05 | 2020-02-05 | 1 | 7 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 79 days
| Finished |  |  | 4.4.9 | Product Purchase List |  | 100% | MTT | 100% | 2020-02-06 | 2020-02-06 | 1 | 7 hr |  | 2019-11-01 | 2019-11-04 |  | 2 days | 62 days
| Finished |  |  | 4.4.10 | Application Status List |  | 100% | MTT | 100% | 2020-02-07 | 2020-02-07 | 1 | 7 hr
| Finished |  |  | 4.4.11 | Loan Calculator |  | 100% | AHO | 100% | 2020-03-16 | 2020-03-18 | 3 | 21 hr
a | Finished |  | P2_4.5 | Coding Development (WEB) | [17 empty] | 0 | 0
| Finished |  |  | 4.5.1 | LGN001 |  | 100% | THHZ | 100% | 2020-02-10 | 2020-02-19 | 7 | 49 hr |  | 2019-09-09 | 2019-09-09 |  | 1 day | 107 days
| Finished |  |  | 4.5.2 | MNU001 |  | 100% | THHZ | 100% | 2020-02-20 | 2020-02-21 | 2 | 14 hr |  | 2019-09-10 | 2019-09-10 |  | 1 day | 108 days
| Finished |  |  | 4.5.3 | MAN001 (Dashboard) |  | 100% | PN | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr |  | 2019-10-09 | 2019-10-17 |  | 4 days | 88 days
| Finished |  |  | 4.5.4 | USR001 |  | 100% | THHZ | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr |  | 2019-09-10 | 2019-09-10 |  | 1 day | 116 days
| Finished |  |  | 4.5.5 | USR002 |  | 100% | THHZ | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr |  | 2019-09-11 | 2019-09-11 |  | 1 day | 124 days
| Finished |  |  | 4.5.6 | USR003 |  | 100% | THHZ | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr |  | 2019-09-12 | 2019-09-12 |  | 1 day | 128 days
| Finished |  |  | 4.5.7 | USR004 |  | 100% | THHZ | 100% | 2020-02-18 | 2020-02-19 | 2 | 14 hr |  | 2019-09-13 | 2019-09-13 |  | 1 day | 103 days
| Finished |  |  | 4.5.8 | USR005 |  | 100% | THHZ | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr |  | 2019-09-14 | 2019-09-14 |  | 0 days | 108 days
| Finished |  |  | 4.5.9 | USR006 |  | 100% | THHZ | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr |  | 2019-09-15 | 2019-09-15 |  | 0 days | 112 days
| Finished |  |  | 4.5.10 | USR007 |  | 100% | THHZ | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr |  | 2019-09-16 | 2019-09-16 |  | 1 day | 121 days
| Finished |  |  | 4.5.11 | USR008 |  | 100% | THHZ | 100% | 2020-02-10 | 2020-02-19 | 7 | 49 hr |  | 2019-09-17 | 2019-09-17 |  | 1 day | 101 days
| Finished |  |  | 4.5.12 | APL001 (List / Cancel) |  | 100% | THHZ | 100% | 2020-02-20 | 2020-02-21 | 2 | 14 hr |  | 2019-09-25 | 2019-09-27 |  | 3 days | 95 days
| Finished |  |  | 4.5.13 | APL002 (Detail) |  | 100% | THHZ | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr |  | 2019-09-30 | 2019-10-02 |  | 3 days | 96 days
| Finished |  |  | 4.5.14 | APL003 (Application List for New Application) |  | 100% | THHZ | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 99 days
| Finished |  |  | 4.5.15 | APL004 (Application List for Indexed Application) |  | 100% | THHZ | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr |  | 2019-10-03 | 2019-10-03 |  | 1 day | 108 days
| Finished |  |  | 4.5.16 | APL005 (Application List for Uploaded Application) |  | 100% | THHZ | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr |  | 2019-10-04 | 2019-10-04 |  | 1 day | 112 days
| Finished |  |  | 4.5.17 | APL006 (Application List for Cancel Application) |  | 100% | THHZ | 100% | 2020-02-18 | 2020-02-19 | 2 | 14 hr |  | 2019-10-04 | 2019-10-04 |  | 1 day | 88 days
| Finished |  |  | 4.5.18 | APL007 (Application List for Document Follow Up Application) |  | 100% | THHZ | 100% | 2020-02-10 | 2020-02-19 | 7 | 49 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 87 days
| Finished |  |  | 4.5.19 | APL008 (Application List for Settled Index Application) |  | 100% | THHZ | 100% | 2020-02-20 | 2020-02-21 | 2 | 14 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 89 days
| Finished |  |  | 4.5.20 | APL009 (Application List for Settled Application) |  | 100% | THHZ | 100% | 2020-02-24 | 2020-02-27 | 4 | 28 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 93 days
| Finished |  |  | 4.5.21 | APL0010 (New Detail) |  | 100% | THHZ | 100% | 2020-02-28 | 2020-03-04 | 3 | 21 hr |  | 2019-10-04 | 2019-10-07 |  | 2 days | 97 days
| Finished |  |  | 4.5.22 | APL0011 (Indexing Detail) |  | 100% | THHZ | 100% | 2020-03-16 | 2020-03-17 | 2 | 14 hr |  | 2019-10-07 | 2019-10-07 |  | 1 day | 106 days
| Finished |  |  | 4.5.23 | APL0012 (Application Upload Detail) |  | 100% | THHZ | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr |  | 2019-10-08 | 2019-10-08 |  | 1 day | 110 days
| Finished |  |  | 4.5.24 | APL0013 (Application Edit Request Detail) |  | 100% | THHZ | 100% | 2020-02-18 | 2020-02-19 | 2 | 14 hr |  | 2019-10-09 | 2019-10-09 |  | 1 day | 85 days
| Finished |  |  | 4.5.25 | APL0014 (Settlement Indexing Detail) |  | 100% | THHZ | 100% | 2020-03-18 | 2020-03-19 | 2 | 14 hr |  | 2019-10-10 | 2019-10-10 |  | 1 day | 105 days
| Finished |  |  | 4.5.26 | APL0015 (Upload Photo Check by Aeon) |  | 100% | THHZ | 100% | 2020-03-20 | 2020-03-23 | 2 | 14 hr |  | 2019-10-10 | 2019-10-17 |  | 3 days | 105 days
| Finished |  |  | 4.5.27 | Schedular |  | 100% | THHZ | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr |  | 2019-10-10 | 2019-10-17 |  | 3 days | 106 days
a | Finished |  | P2_4.6 | JAR Modification
a | Finished |  |  | 4.6.1 | Import JAR |  | 100% | HWYK | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr | [8 empty] | 7 | #VALUE!
| Finished |  |  | 4.6.2 | Export JAR |  | 100% | HWYK | 100% | 2020-03-24 | 2020-03-24 | 1 | 7 hr
a | In Progress |  | P2_4.3 | Coding Development(WEB Client) | [17 empty] | 0 | 0
| In Progress |  |  | 4.3.1 | Project received date from Aceplus |  | 100% | PN | 100% | 2020-03-18 | 2020-03-26 | 7 | 49 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 102 days
| In Progress |  |  | 4.3.1 | New User Digital Application Apply |  | 100% | PN | 100% | 2020-03-16 | 2020-03-26 | 9 | 63 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 102 days
| In Progress |  |  | 4.3.1 | New User Digital Application Combination with Aceplus Project |  | 100% | PN | 100% | 2020-03-30 | 2020-04-08 | 8 | 56 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 111 days
| In Progress |  |  | 4.3.1 | Digital Application Apply Modification |  | 100% | PN | 100% | 2020-04-09 | 2020-04-29 | 9 | 63 hr |  | 2019-10-24 | 2019-10-25 |  | 2 days | 126 days
| In Progress |  |  | 4.3.2 | Digital Application List Modification |  | 100% | PN | 100% | 2020-04-30 | 2020-05-11 | 6 | 42 hr
| In Progress |  |  | 4.3.3 | Digital Application Detail Modification |  | 100% | PN | 100% | 2020-05-12 | 2020-05-20 | 7 | 49 hr
| In Progress |  |  | 4.3.3 | Product Purchase Detail Modification |  | 100% | PN | 100% | 2020-05-21 | 2020-06-01 | 8 | 56 hr
a |  | P2_5 | Unit Testing (Andriod)
| Not Started Yet |  | P2_5.1 | Test Spec Creation
a | Not Started Yet |  |  | 5.1.1 | Mobile Test Spec - DA, VCS, ATS, ATCS |  | 100% | HWYK | 100% | 2020-04-21 | 2020-04-24 | 4 | 28 hr | [8 empty] | 28 | #VALUE!
| Finished |  | P2_5.2 | Test Execution
| Finished |  |  | 5.2.1 | Mobile (Andriod) - 1 |  | 100% | SSS | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr |  |  |  |  | 3 | 31286 days
| Finished |  |  | 5.2.2 | WEB - 1 |  | 100% | THHZ | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr
| Finished |  |  | 5.2.3 | Bug Fixed (Andriod) - 1 |  | 100% | AHO | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr
| Finished |  |  | 5.2.4 | Bug Fixed (WEBService) -1 |  | 100% | HWYK | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr
| Finished |  |  | 5.2.5 | Bug Fixed (WEB) - 1 |  | 100% | THHZ | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr
| Finished |  |  | 5.2.6 | Mobile (Andriod) - 2 |  | 100% | SSS | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr |  |  |  |  | 3 | 31286 days
| Finished |  |  | 5.2.7 | WEB - 2 |  | 100% | THHZ | 100% | 2020-03-12 | 2020-03-25 | 10 | 70 hr
| Not Started Yet |  |  | 5.2.8 | Bug Fixed (Andriod - DA) - 2 |  | 100% | AHO | 100% | 2020-03-30 | 2020-04-06 | 6 | 42 hr
| Not Started Yet |  |  | 5.2.9 | Bug Fixed (Andriod - AT) - 2 |  | 100% | AHO | 100% | 2020-04-07 | 2020-04-08 | 2 | 14 hr
| Not Started Yet |  |  | 5.2.10 | Bug Fixed (WEBService) - 2 |  | 100% | HWYK | 100% | 2020-04-27 | 2020-04-29 | 3 | 21 hr
| Not Started Yet |  |  | 5.2.11 | Bug Fixed (WEB) - 2 |  | 100% | THHZ | 100% | 2020-03-30 | 2020-04-03 | 5 | 35 hr
a |  | P2_6 | Unit Testing (iOS)
| Not Started Yet |  | P2_6_1.1 | Test Execution
| Not Started Yet |  |  | 6_1.1.1 | Mobile (iOS) |  | 0% | KMS | 100% | 2020-06-11 | 2020-06-17 | 5 | 35 hr |  |  |  |  | 1 | 31337 days
| Not Started Yet |  |  | 6_1.1.2 | WEB + JAR + Schedular |  | 0% | THHZ | 100% | 2020-06-11 | 2020-06-17 | 5 | 35 hr
| Not Started Yet |  |  | 6_1.1.3 | Bug Fixed (iOS) |  | 0% | KMS | 100% | 2020-06-18 | 2020-06-25 | 6 | 42 hr
| Not Started Yet |  |  | 6_1.1.4 | Bug Fixed (WEBService) |  | 0% | HWYK | 100% | 2020-06-12 | 2020-06-17 | 4 | 28 hr
| Not Started Yet |  |  | 6_1.1.5 | Bug Fixed (WEB + JAR + Schedular) |  | 0% | HWYK | 100% | 2020-06-18 | 2020-06-23 | 4 | 28 hr
a |  | P2_7 | Unit Testing (Angular)
| Not Started Yet |  | P2_7_1.1 | Test Execution
| Not Started Yet |  |  | 7_1.1.1 | Angular + WEB + JAR + Schedular |  | 0% | PN, THHZ, AHO, HWYK | 100% | 2020-06-02 | 2020-06-08 | 5 | 35 hr |  |  |  |  | 1 | 31330 days
| Not Started Yet |  |  | 7_1.1.2 | WEB + JAR + Schedular |  | 0% | THHZ | 100% | 2020-06-02 | 2020-06-08 | 5 | 35 hr
| Not Started Yet |  |  | 7_1.1.3 | Bug Fixed (Angular) |  | 0% | PN | 100% | 2020-06-09 | 2020-06-16 | 6 | 42 hr
| Not Started Yet |  |  | 7_1.1.4 | Bug Fixed (WEBService) |  | 0% | HWYK | 100% | 2020-06-04 | 2020-06-08 | 3 | 21 hr
| Not Started Yet |  |  | 7_1.1.5 | Bug Fixed (WEB + JAR + Schedular) |  | 0% | HWYK | 100% | 2020-06-09 | 2020-06-11 | 3 | 21 hr
a |  | P2_6 | Integration Testing
| Not Started Yet |  | P2_6.1 | Test Spec Creation
a | Not Started Yet |  |  | 6.1.1 | Test Spec Creation |  | 0% | HWYK | 100% | 2020-04-30 | 2020-05-11 | 6 | 42 hr | [8 empty] | 42 | #VALUE!
| Not Started Yet |  | P2_6.2 | Test Execution - Mobile (iOS/Andriod) + Web + JAR
| Not Started Yet |  |  | 6.2.1 | Mobile (Andriod) + Web + JAR + Schedular - 2 |  | 0% | AHO, SSS | 100% | 2020-06-26 | 2020-07-01 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.2 | Mobile (iOS) + Web + JAR + Schedular |  | 0% | KMS, THHZ | 100% | 2020-06-26 | 2020-07-01 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.3 | WEB Client |  | 0% | PN | 100% | 2020-06-26 | 2020-07-01 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.4 | Bug Fixed (Andriod) |  | 0% | AHO | 100% | 2020-07-02 | 2020-07-07 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.5 | Bug Fixed (iOS) |  | 0% | KMS | 100% | 2020-07-02 | 2020-07-07 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.6 | Bug Fixed (Angular) |  | 0% | PN | 100% | 2020-07-02 | 2020-07-07 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.7 | Bug Fixed (ASS Andriod) |  | 0% | SSS | 100% | 2020-07-02 | 2020-07-07 | 4 | 28 hr
| Not Started Yet |  |  | 6.2.8 | Bug Fixed (WEBService) |  | 0% | HWYK | 100% | 2020-06-30 | 2020-07-02 | 3 | 21 hr
| Not Started Yet |  |  | 6.2.9 | Bug Fixed (WEB + JAR + Schedular) |  | 0% | HWYK | 100% | 2020-07-03 | 2020-07-07 | 3 | 21 hr
a |  | P2_7 | Performance Testing
| Cancel |  | P2_7.1 | Test Spec Creation
a | Cancel |  |  | 7.1.1 | Test Spec Creation | [16 empty] | 0 | 0
| Cancel |  | P2_7.2 | Test Execution
| Cancel |  |  | 7.2.1 | Mobile (Andriod) (News, Promotion, Coupon)
| Cancel |  |  | 7.2.2 | Mobile (iOS) (News, Promotion, Coupon)
| Cancel |  |  | 7.2.3 | Web Service
| Cancel |  |  | 7.2.4 | Web
a | In Progress | P2_8 | User Training
a | In Progress |  | P2_8.1 | User Manual Preparation | [17 empty] | 0 | 0
| In Progress |  |  | 8.1.1 | DA Web User Manual Creation |  | 0% | THHZ | 100% | 2020-04-06 | 2020-04-21 | 6 | 42 hr
| In Progress |  |  | 8.1.1 | ATS Web User Manual Creation |  | 0% | THHZ | 100% | 2020-04-22 | 2020-04-27 | 4 | 28 hr
| In Progress |  |  | 8.1.1 | ATCS Web User Manual Creation |  | 0% | THHZ | 100% | 2020-04-28 | 2020-04-30 | 3 | 21 hr
| In Progress |  |  | 8.1.1 | VCS Web User Manual Creation |  | 0% | THHZ | 100% | 2020-05-04 | 2020-05-07 | 3 | 21 hr
| In Progress |  |  | 8.1.2 | Mobile User Manual Creation |  | 0% | THHZ | 100% | 2020-05-08 | 2020-05-13 | 4 | 28 hr
a | In Progress | P2_8_1 | UAT
a | In Progress |  | 8_1.1.1 | Test Execution | [17 empty] | 0 | 0
| Finished |  |  | 8_1.1.1 | Andriod 1 |  | 0% | Aeon | 100% | 2020-03-18 | 2020-03-20 | 3 | 21 hr |  | 2020-03-18 | 2020-03-25 |  | 6 days | 3 days
| Not Started Yet |  |  | 8_1.1.2 | iOS |  |  |  | 100%
| Relocated |  |  | 8_1.1.3 | Bug Fixed (Andriod) |  |  |  | 100%
| Relocated |  |  | 8_1.1.4 | Bug Fixed (iOS) |  |  |  | 100%
| Relocated |  |  | 8_1.1.5 | Bug Fixed (WEBService) |  |  |  | 100%
| Relocated |  |  | 8_1.1.6 | Bug Fixed (WEB) |  |  |  | 100%
| Relocated |  |  | 8_1.1.7 | Andriod 2 |  |  |  | 100%
| Relocated |  |  | 8_1.1.8 | Andriod 3 |  |  |  | 100%
| Relocated |  |  | 8_1.1.9 | Andriod 4 |  |  |  | 100%
a | Not Started Yet | P2_9 | Implementation (Production Released)
a | Not Started Yet |  | P2_9.1 | Preparation | [17 empty] | 0 | 0
| Not Started Yet |  |  | 9.1.1 | DDL + DML Revise |  |  |  | 100%
| Not Started Yet |  |  | 9.1.2 | WAR Deployment Rehearsal |  |  |  | 100%
| Not Started Yet |  |  | 9.1.3 | Web service Deployment Rehearsal |  |  |  | 100%
| Not Started Yet |  |  | 9.1.4 | WAR Deployment + DB Released |  |  |  | 100%
a | Not Started Yet |  | P2_9.1 | WEB | [17 empty] | 0 | 0
| Not Started Yet |  |  | 9.1.4 | Webservice Released |  |  |  | 100%
a | Not Started Yet |  | P2_9.2 | Release APK | [17 empty] | 0 | 0
| Not Started Yet |  |  | 9.2.1 | Prepared for Release_iOS Test Flight |  |  |  | 100%
| Not Started Yet |  |  | 9.2.2 | Andriod Released to Play Store for Testing
| Not Started Yet |  |  | 9.2.3 | iOS Released to Apple Store Test Flight |  |  |  | 100%
a | Not Started Yet |  |  | 9.2.4 | DAT User Test | [16 empty] | 0 | 0
| Not Started Yet |  |  | 9.2.5 | Prepared for Release (Andriod) |  |  |  | 100%
| Not Started Yet |  |  | 9.2.6 | Prepared for Release (iOS) |  |  |  | 100%
| Not Started Yet |  |  | 9.2.7 | Andriod Released to Play Store |  |  |  | 100%
| Not Started Yet |  |  | 9.2.8 | iOS Released to Apple Store |  |  |  | 100%
a | Not Started Yet | P2_10 | Reverse Engineering
a | Not Started Yet |  | P4_1 | HTML Mock | [17 empty] | 0 | 0
| Not Started Yet |  |  | 4.4.1 | Web (DA)
| Not Started Yet |  |  | 4.4.1.1 | All Screens |  | 0% | SSS | 100% | 2020-03-26 | 2020-04-07 | 8 | 56 hr
| Not Started Yet |  |  | 4.4.2 | Web (ATS) |  |  |  | 100%
| Not Started Yet |  |  | 4.4.2.1 | All Screens |  | 0% | SSS | 100% | 2020-04-08 | 2020-04-21 | 4 | 28 hr
| Not Started Yet |  |  | 4.4.3 | Web (ATCS) |  |  |  | 100%
| Not Started Yet |  |  | 4.4.3.1 | All Screens |  | 0% | SSS | 100% | 2020-04-22 | 2020-04-24 | 3 | 21 hr
| Not Started Yet |  |  | 4.4.4 | Web (ASS) |  |  |  | 100%
| Not Started Yet |  |  | 4.4.4.1 | All Screens |  | 0% | SSS | 100% | 2020-04-27 | 2020-04-29 | 3 | 21 hr
a | Not Started Yet |  | P2_4.5 | Specification |  |  |  |  | 100% | [12 empty] | 0 | 0
| Not Started Yet |  |  | 4.5.1 | RD |  |  |  | 100%
| Not Started Yet |  |  | 4.5.1.1 | Requirement Definition - Change Log |  | 0% | PWH |  | 2020-03-26 | 2020-04-01 | 4 | 0 hr
| Not Started Yet |  |  | 4.5.2 | Basic Design |  |  |  | 100%
| Finished |  |  | 4.5.2.1 | Screen List |  | 0% | THHZ | 100% | 2020-05-14 | 2020-05-15 | 2 | 14 hr
| Not Started Yet |  |  | 4.5.3 | Detail Design |  |  |  | 100%
| Not Started Yet |  |  | 4.5.3.1 | Business Spec (WEB) - DA |  | 0% | THHZ | 100% | 2020-05-18 | 2020-05-26 | 7 | 49 hr
| Not Started Yet |  |  | 4.5.3.2 | Business Spec (WEB) - ATCS |  | 0% | THHZ | 100% | 2020-05-27 | 2020-06-01 | 4 | 28 hr
| Not Started Yet |  |  | 4.5.3.3 | Business Spec (WEB) - ATS |  | 0% | THHZ | 100% | 2020-06-18 | 2020-06-23 | 4 | 28 hr
| Not Started Yet |  |  | 4.5.3.4 | Business Spec (WEB) - VCS |  | 0% | THHZ | 100% | 2020-06-24 | 2020-06-25 | 2 | 14 hr
| Not Started Yet |  |  | 4.5.3.5 | Business Spec (Mobile)
| Not Started Yet |  |  |  | 4.5.3.5.1 | VCS - Mobile | 0% | SSS | 100% | 2020-04-30 | 2020-05-13 | 8 | 56 hr
| Not Started Yet |  |  |  | 4.5.3.2.2 | ASS - Mobile | 0% | SSS | 100% | 2020-05-14 | 2020-05-21 | 6 | 42 hr
| Not Started Yet |  |  |  | 4.5.3.2.3 | VCS - Web Service | 0% | SSS | 100% | 2020-05-22 | 2020-05-29 | 6 | 42 hr
| Not Started Yet |  |  |  | 4.5.3.2.4 | ASS - - Web Service | 0% | SSS | 100% | 2020-06-01 | 2020-06-09 | 7 | 49 hr
| Not Started Yet |  |  | 4.5.4 | Program Design
| Not Started Yet |  |  | 4.5.4.1 | Status Workflow |  | 0% | HWYK | 100% | 2020-03-31 | 2020-03-31 | 1 | 7 hr |  |  |  |  | 1 | 31289 days
| Not Started Yet |  |  | 4.5.4.2 | Application Process Flow |  | 0% | HWYK | 100% | 2020-04-01 | 2020-04-02 | 2 | 14 hr |  |  |  |  | 1 | 31291 days
| Not Started Yet |  |  | 4.5.5 | DDL, DML
| Not Started Yet |  |  | 4.5.5.1 | DDL, DML |  | 0% | HWYK | 100% | 2020-03-30 | 2020-03-30 | 0.5 | 3.5 hr
| Not Started Yet |  |  | 4.5.6 | Logical ERD Update
| Not Started Yet |  |  | 4.5.6.1 | Logical ERD of VCS |  | 0% | HWYK | 100% | 2020-03-26 | 2020-03-26 | 1 | 7 hr
| Not Started Yet |  |  | 4.5.6.2 | Logical ERD of ASS |  | 0% | HWYK | 100% | 2020-03-30 | 2020-03-30 | 0.5 | 3.5 hr
a | Not Started Yet | P2_12 | Source Import to Git
a | Not Started Yet |  | P2_12.1 | iOS |  |  | 0% | HWYK | 100% | 2020-03-25 | 2020-03-25 | 1 | 7 hr | [8 empty] | 7 | #VALUE!
a | Finished |  | P2_12.2 | Angular |  |  | 0% | HWYK | 100% | 2020-03-25 | 2020-03-25 | 1 | 7 hr | [8 empty] | 7 | #VALUE!
a | Not Started Yet | P2_13 | Improvement Training
a | Not Started Yet |  | P2_13.1 | Import/Export tool training/sharing |  |  | 0% |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_13.2 | J2EE Framework training/sharing |  |  | 0% |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_13.3 | Angular/Javascript Training |  |  | 0% |  | 100% | [12 empty] | 0 | 0
a | Not Started Yet |  | P2_13.4 | Chat server training/sharing |  |  | 0% |  | 100% | [12 empty] | 0 | 0

## Resources
PWH
KYDT
AHO
THHZ
MTT
Blank

## Revision History
Revision History
No | Version | Revision Date | Reviser | The content/ The reason of revise
1 | template | 2016-12-06 | Tin Wint Wint Phyu | Created template.
2 | template | 2017-01-17 | Tin Wint Wint Phyu | Updated template ( add automatci gantt chart ).
3 | 1.0 | 2019-01-29 | Pwint Wai Hlaing | Created ver 1.0.

## Holidays
Holidays in Myanmar for 2014 |  |  |  | Effective Hour | 7
OCT | 2014-10-23 | Diwali Day | 2014-10-23
NOV | 2014-11-06 | Full Moon Day of Tazaungmone | 2014-11-06
DEC | 2014-12-25 | Christmas Day | 2014-12-25
Holidays in Myanmar for 2015
JAN | 2015-01-01 | New Year Day | 2015-01-01
| 2015-01-12 | DAT Trip | 2015-01-12
FEB | 2015-02-12 | Union Day | 2015-02-12
MAR | 2015-03-02 | Peasants' Day | 2015-03-02
| 2015-03-04 | Full Moon Day of Tabaung | 2015-03-04
| 2015-03-27 | Armed Forces Day | 2015-03-27
APR | 2015-04-13 | Water Festival Holidays | 2015-04-13
| 2015-04-14 | Water Festival Holidays | 2015-04-14
| 2015-04-15 | Water Festival Holidays | 2015-04-15
| 2015-04-16 | Water Festival Holidays | 2015-04-16
| 2015-04-17 | Water Festival Holidays | 2015-04-17
| 2015-04-18 | Water Festival Holidays | 2015-04-18
| 2015-04-19 | Water Festival Holidays | 2015-04-19
| 2015-04-20 | Water Festival Holidays | 2015-04-20
| 2015-04-21 | Water Festival Holidays | 2015-04-21
MAY | 2015-05-01 | May Day | 2015-05-01
JULY | 2015-07-31 | Full Moon Day of Waso | 2015-07-31
OCT | 2015-10-28 | Full Moon Day of Thadingyut | 2015-10-28
NOV | 2015-11-26 | Full Moon Day of Tazaungmone | 2015-11-26
DEC | 2015-12-25 | Christmas Day | 2015-12-25
Holidays in Myanmar for 2016
JAN | 2016-01-04 | Independence Day | 2016-01-04
FEB | 2016-02-12 | Union Day | 2016-02-12
MAR | 2016-03-02 | Peasants' Day | 2016-03-02
MAR | 2016-03-23 | Full Moon Day of Tabaung | 2016-03-23
APR | 2016-04-11 | Water Festival Holidays | 2016-04-11
| 2016-04-12 | Water Festival Holidays | 2016-04-12
| 2016-04-13 | Water Festival Holidays | 2016-04-13
| 2016-04-14 | Water Festival Holidays | 2016-04-14
| 2016-04-15 | Water Festival Holidays | 2016-04-15
| 2016-04-16 | Water Festival Holidays | 2016-04-16
| 2016-04-17 | Water Festival Holidays | 2016-04-17
| 2016-04-18 | Water Festival Holidays | 2016-04-18
| 2016-04-19 | Water Festival Holidays | 2016-04-19
| 2016-04-20 | Water Festival Holidays | 2016-04-20
JULY | 2016-07-19 | Martyrs' Day, Full Moon Day of Waso | 2016-07-19
SEPT | 2016-09-13 | Eid Day | 2016-09-13
NOV | 2016-11-14 | Full Moon Day of Tazaungmone | 2016-11-14
| 2016-11-24 | National Day | 2016-11-24
DEC | 2016-12-29 | Kayin New Year | 2016-12-29
Holidays in Myanmar for 2017
JAN | 2017-01-04 | Independence Day | 2017-01-04
MAR | 2017-03-02 | Peasants' Day | 2017-03-02
| 2017-03-27 | Armed Forces Day | 2017-03-27
APR | 2017-04-13 | Water Festival Holidays | 2017-04-13
| 2017-04-14 | Water Festival Holidays | 2017-04-14
| 2017-04-15 | Water Festival Holidays | 2017-04-15
| 2017-04-16 | Water Festival Holidays | 2017-04-16
| 2017-04-17 | Water Festival Holidays | 2017-04-17
May | 2017-05-01 | May Day | 2017-05-01
| 2017-05-10 | Full Moon Day of Kasong | 2017-05-10
JULY | 2017-07-19 | Martyrs' Day | 2017-07-19
October | 2017-10-04 | Thadinkyut Full Moon Holiday | 2017-10-04
| 2017-10-05 | Thadinkyut Full Moon Holiday | 2017-10-05
| 2017-10-06 | Thadinkyut Full Moon Holiday | 2017-10-06
| 2017-10-18 | Diwali/Deepavali | 2017-10-18
November | 2017-11-02 | Tasaungmone Full Moon Holiday | 2017-11-02
| 2017-11-03 | Tasaungmone Full Moon Holiday | 2017-11-03
| 2017-11-13 | National Day | 2017-11-13
December | 2017-12-18 | Kayin New Year Day | 2017-12-18
| 2017-12-25 | Chiristmas Day | 2017-12-25
| 2017-12-30 | International New Year Holidays | 2017-12-30
| 2017-12-31 | International New Year Holidays | 2017-12-31
Holidays in Myanmar for 2019
JAN | 2019-01-01 | International New Year’s Day | 1st January, Tuesday
| 2019-01-04 | Independence Day | 4th January, Friday
| 2019-01-07 | Kayin New Year Day | 6th January, Sunday
FEB | 2019-02-12 | Union Day | 12th February, Tuesday
MAR | 2019-03-02 | Peasant’s Day | 2nd March, Saturday
| 2019-03-20 | Full moon Day of Tabaung | 20th March, Wednesday
| 2019-03-27 | Armed Forces Day | 27th March, Wednesday
APR | 2019-04-01 | Bank Holiday | 1st April, Monday
| 2019-04-13 | Thingyan Festival | 13th April, Saturday
| 2019-04-14 | Thingyan Festival | 14th April, Sunday
| 2019-04-15 | Thingyan Festival | 15th April, Monday
| 2019-04-16 | Thingyan Festival | 16th April, Tuesday
| 2019-04-17 | Myanmar New Year Day | 17th April, Wednesday
MAY | 2019-05-01 | World Worker’s Day | 1st May, Wednesday
| 2019-05-18 | Full Moon Day of Kasong | 18th May, Saturday
JUL | 2019-07-16 | Full Moon Day of Waso | 16th July, Tuesday
| 2019-07-19 | Martyr’s Day | 19th July, Friday
|  | Eid Holiday | * TBD
OCT | 2019-10-01 | Bank Holiday | 1st October, Tuesday
| 2019-10-12 | Thadingyut Festival | 12th October, Saturday
| 2019-10-13 | Full Moon Day of Thadingyut | 13th October, Sunday
| 2019-10-14 | Thadingyut Festival | 14th October, Monday
* TBD
NOV | 2019-11-10 |  | 10th November, Sunday
| 2019-11-11 |  | 11th November, Monday
| 2019-11-21 |  | 21st November, Thursday
DEC | 2019-12-25 |  | 25th December, Wednesday
| 2019-12-26 |  | 26th December, Thursday
| 2019-12-31 |  | 31st December, Tuesday
Holidays in Myanmar for 2020
JAN | 2020-01-01 | International New Year's Day
| 2020-01-06 | Substitute of Independence Day
FEB | 2020-02-12 | Union Day
MAR | 2020-03-02 | Peasent Day
| 2020-03-09 | Full Moon Day of Tabaung
| 2020-03-27 | Armed Forces Day
APR | 2020-04-10 | Thingyan Holiday
| 2020-04-13 | Thingyan Holiday
| 2020-04-14 | Thingyan Holiday
| 2020-04-15 | Thingyan Holiday
| 2020-04-16 | Thingyan Holiday
| 2020-04-17 | Thingyan Holiday
MAY | 2020-05-01 | World Worker’s Day
| 2020-05-06 | Full Moon Day of Kasong
JUL | 2020-07-20 | Martyr’s Day

## Not Available
Assign Status
Not Started Yet
In Progress
Finished
Early Finished
Late Finished
Delay
Relocated
Cancel
Delivery Status
Extend
Delivered